## Sheet1
State Agency Directors Approval: |  | Date:
Project Coordinator Approval: |  | Date:
Project Name: |  | DBA Project #:
Substantial Completion Date: |  | Occupancy Date:
ITEM |  | DATE REC'D | INITIALS
1 | PROJECT BID RELATED DOCUMENTS
a) Bid Documents for A&E Professional Services Contract
1) Request for Proposal
2) Proof of Advertisement(s)
3) Panel Evaluations of Proposal
4) DBA, DFA Approval to Award Documents
b) Pre-Bid Plan Submittals and DBA Responses
c) Full Set of Approved Plans & Specifications (including division zero documents)
d) Bid Documents
1) Project Disclosure Statement
2) Invitation for Bid
3) Proof of Advertisement(s)
4) Bid Addendums
e) Bids Received
1) Bid Security
f) Certified Bid Tabulation
g) Negotiated Changes
h) Intent to Award
2 | CONTRACTS & AGREEMENTS
a) A&E Professional Services Contract
b) General Contractors Agreement with Owner
c) Performance and Payment Bond
d) Certificates of Insurance and Policies
e) Notice to Proceed
f) EO 98-04 Contract and Grant Disclosure Form(s): Contractor and Subcontractors
g) Change Orders
h) Maintenance and/or Service Contract(s)
3 | CLOSE-OUT DOCUMENTS
a) Substantial Completion Form
* | b) Certificate of Final Completion
* | c) Application for Final Payment
* | d) Release of Lien
* | e) Consent of Surety
f) Certificate of Occupancy
* | g) Agency's Request for Final Payment
* | h) Design Professional Closeout Certification
i) Agency's Decision Regarding Assessing Liquidated Damages
4 | DESIGNED PROFESSIONAL / CONTRACTOR SUPPLIED CLOSE-OUT DOCUMENTS
a) Roof Warranty from Manufacture (two copies)
1) Manufactures Inspection of Roof Installation and Final Inspection
2) Inspect Roof 30 Days Prior to Manufactures Warranty
b) Contractors Two-Year Labor Warranty on Roof Installation
1) Inspect Roof 60 Days Prior Warranty Expiration
c) Maintenance and Operation Manuals (HVAC, equipment etc.) and Catalog Data
d) Final Plumbing Inspection by DHS Inspector
e) Record Drawings (as built drawings)
f) CD-Rom with All Contract Documents, Record Drawings, Specifications, etc.
g) Contractors One Year Workmanship, Materials Warranty
1) Inspect Project 30 Days Prior to Warranty Expiration
h) Termite Inspection Certificate
i) Certificate of Air Balance
j) Final HVAC Inspection by DHS Inspector
k) LEED Documentation
l) Facility Key Log
m) Miscellaneous Equipment and System Warranty(s)
n) Contractor Supplied Training on Equipment and Systems (with sign-in sheets)
o) Videos/CD's and Training Manuals on Controls, HVAC, and Equipment
p) Equipment and System Inspections Reports:
1) Boiler and Tank
2) Elevators and Hoist Systems
3) Backflow Preventers on Potable Water, Fire Suppression, HVAC, Misc. Equip.
4) Fire Suppression System
5) Fire Alarm System
6) Security System
7) Backup Power Generator
8) Cable Test/Certification Reports and Startup Records
q) Contractor Provided Written Instructions on Seasonal Adjustments
r) Mechanical System Balance Once Per Each Major Season Change; 1st year
5 | MISCELLANEOUS
a) Project Correspondence (meeting minutes, emails, etc.)
b) DBA Observers Reports
c) Design Professionals Inspection Reports
d) State Inspectors Reports
e) Owners Inspection Reports
f) Progress Photos
g) Progress Payments With Backup Documentation
h) Post-Bid Plan Review Submittals and Responses From DBA
i) Predesign Project Studies
j) Future Maintenance and Operational Cost Studies
k) Environmental Studies and Reports
l) Floodplain Management Plans and Programs
Notes: